MVP Build & Shopify App Store Launch Plan

Self-serve loyalty & rewards app — from Partner account to live listing

Prepared for Gida  |  August 12, 2026

# 1. Scope: what the MVP actually needs to do

Pulled directly from the competitor matrix and the real merchant complaints gathered from Smile.io and LoyaltyLion's Shopify reviews. Anything not on this list is deliberately out of scope for v1 — resist adding it.

## Must-have (v1 launch blockers)

- Points ledger: earn points on purchase (configurable rate), redeem points as a discount at checkout.

- VIP tiers: 2-3 configurable spend/order thresholds with different earn multipliers.

- Referral program built into the same ledger — refer a friend, both sides earn points on the referred purchase. No separate app, no separate fee.

- Flat, published, self-serve pricing with no order-count cliff — one plan, one price, clearly stated feature set (directly answers the Smile.io 'starter plan trap' and 'nothing included in $49' complaints).

- True self-serve cancel: a working Cancel button in the app's own settings page that immediately stops billing — not a support-ticket-only flow (directly answers the LoyaltyLion 'impossible to cancel' complaints from HouseofDogs.no and Blink outside the box).

- Automatic refund clawback: when an order is refunded, the points it earned are automatically reversed via webhook, no manual merchant action (directly answers CB Hobby's Smile.io complaint).

- Basic referral fraud protection: rate-limit code generation per customer, expire unused codes, alert on abnormal code-creation volume (directly answers Karine Sultan's 12,000-leaked-codes complaint).

## Should-have (differentiator, build if timeline allows)

- Cadence-based reward triggers for replenishment/subscription brands: bonus points or a nudge when a customer's reorder is overdue relative to their historical purchase cadence, not just raw order count. This is the feature none of the four incumbents in the competitor matrix are built around.

## Explicitly out of scope for v1

- POS / in-person redemption sync (flagged as broken even on paid Smile.io — treat as a v2 problem once core web flow is proven).

- Multi-language / translation tooling (BON Loyalty already owns this niche well; not the wedge for v1).

- Custom landing pages / deep marketing automation (this is what pushes Smile.io users to their $199 tier — explicitly the complexity you are avoiding).

# 2. Tech stack

Solo-buildable stack, consistent with the tools named in your original brief (Cursor / Claude Code) and Shopify's current recommended path as of August 2026:

- Shopify CLI + the official app template, scaffolded with React Router (Shopify's current guidance: new apps should use React Router, not the older Remix template, even though the underlying package is still named shopify-app-remix).

- Shopify Admin GraphQL API for orders, customers, and discounts; Polaris for every embedded admin screen (required for approval, not optional).

- Theme App Extension (app embed block) for the storefront points widget — installs into any Online Store 2.0 theme from the Theme Editor with zero manual theme-code edits, which is what lets a merchant self-serve install in minutes.

- Checkout UI Extension for point redemption at checkout ('pay with points' style flow). Note: Shopify Scripts are fully deprecated as of June 30, 2026 — there is no legacy fallback here, the extension-based approach is the only supported path.

- Shopify App Pricing (the current managed billing product, which has superseded the older Billing API) for the recurring monthly charge — it handles proration, free trials, and plan changes for you rather than you coding charge logic by hand.

- A small managed Postgres instance (e.g. Supabase or Railway) for the points ledger and cadence-tracking data that lives outside Shopify's own data model.

# 3. Build phases

| Phase | Timeframe | What happens | Exit criteria |
| --- | --- | --- | --- |
| 0. Setup | Days 1-3 | Create free Shopify Partner account; create a development store; install Node LTS; scaffold the app with Shopify CLI; stand up the Postgres instance; confirm OAuth install flow works end-to-end on the dev store. | App installs on dev store and shows an empty Polaris admin screen |
| 1. Core ledger | Week 1-2 | Build the points ledger (earn/redeem), VIP tier logic, and the merchant-facing Polaris settings screens (earn rate, tier thresholds, plan/pricing display). | Merchant can configure a program end-to-end in the dev store admin |
| 2. Storefront + checkout | Week 2-3 | Build the Theme App Extension for the points widget and the Checkout UI Extension for redemption. Wire referral code generation and redemption into the same ledger. | A test customer can see their points on-site, refer a friend, and redeem points at checkout in the dev store |
| 3. Differentiators | Week 3-4 | Add automatic refund-clawback webhook handler, referral fraud rate-limiting, the true self-serve cancel flow, and (if time allows) the cadence-based reward trigger. | All 6 must-have items from Section 1 verified working |
| 4. Billing + compliance | Week 5 | Integrate Shopify App Pricing for the flat monthly plan; implement and test the 3 mandatory GDPR webhooks plus app/uninstalled; verify HMAC signature checks on every webhook. | Billing charges correctly in test mode; all compliance webhooks return 200 within Shopify's test harness |
| 5. Listing assets | Week 6 | Populate the dev store with realistic demo data; capture 4-7 screenshots; write the 5 required listing-copy fields (tagline, value prop, features, how it works, pricing); record the English-language demo screencast; set an emergency developer contact. | Everything on Shopify's App Requirements Checklist is complete |
| 6. Submit + review | Week 6-9 | Submit for review via the Partner Dashboard. Typical review takes roughly 2-4 weeks (some apps clear in 5-10 business days depending on submission volume and app complexity). Respond quickly to any rejection — broken privacy webhooks are the single most common first-time rejection reason. | App status reaches Published |
| 7. Launch | Week 9+ | Go live. Immediately reach out to the merchants on the Outreach Targets list from the research spreadsheet — especially the ones actively switching (Avernic Smoke Shop) — to seed your first 15-20 reviews, since review count/rating drives App Store ranking directly. | First paying merchants installed, review flywheel started |

This is roughly 9 weeks solo, working at a realistic pace with AI-assisted coding (Cursor/Claude Code) doing the bulk of the implementation while you handle architecture decisions, testing, and merchant outreach. Compress phases 1-3 if you cut the cadence-based differentiator from v1 and ship it as a fast-follow update instead — reasonable if you want to get listed sooner and iterate in public.

# 4. Shopify App Store submission checklist

Everything below has to be true before you submit — treat it as a literal gate, not a guideline:

- Three mandatory compliance webhooks implemented and tested: customers/data_request, customers/redact, shop/redact — plus app/uninstalled. All return correctly signed, verified HMAC responses.

- Billing integrated via Shopify App Pricing (GraphQL), with a published, single, transparent monthly price — no hidden tiers.

- All embedded admin screens built with Polaris components and the latest Shopify App Bridge version.

- App fully installable and functional on a development store using only publicly documented APIs.

- Listing copy written for all 5 required fields: tagline, value proposition, feature list, how-it-works, and pricing.

- 4-7 screenshots captured showing real (or realistic demo) merchant data, not empty states.

- A demo screencast recorded in English (or with English subtitles) walking through onboarding and core features.

- Valid test credentials provided to Shopify's review team with full feature access.

- An up-to-date emergency developer contact set in the Partner Dashboard.

- Primary listing language specified and at least one App Store listing created.

Optional, post-launch: the 'Built for Shopify' badge (extra trust signal in search results) requires meeting additional performance (storefront speed impact under 10 points), design, and integration bars, and adds its own 2-4 week review on top of standard approval. Don't chase it for v1 — revisit once you have paying merchants and real performance data.

# 5. First 30 days after going live

- Work the Outreach Targets list from the research spreadsheet directly — lead with Avernic Smoke Shop and the other merchants who explicitly said they're switching or got hit with a surprise price increase.

- Ask your first 10-15 installs for a Shopify App Store review before asking for anything else — review count and rating are the single biggest lever on organic App Store ranking.

- Run the Bending Spoons habit at solo scale: ship one small pricing, onboarding, or copy experiment per week and track install → activation → paid conversion, rather than treating launch as a finish line.

- Watch for the two failure modes documented in this research: don't let redemption UX get confusing (the #1 complaint against every incumbent), and don't let support response time slip past 24 hours even while you're the only person answering tickets.

# Sources

Shopify CLI / app scaffolding: shopify.dev app-remix package, Braincuber getting-started guide

Shopify App Pricing / billing: shopify.dev App Pricing, appSubscriptionCreate mutation

Mandatory compliance webhooks: shopify.dev privacy law compliance, Digital Heroes submission checklist

App Store submission & review process: shopify.dev submit for review, shopify.dev review process, Gadget.dev review guide

Theme App Extensions / storefront widgets: Folio3 theme app extensions guide

Checkout UI Extensions / points redemption / Scripts deprecation: shopify.dev discounts, Skailama discount functions guide

Built for Shopify badge requirements: shopify.dev Built for Shopify requirements, Help Center overview